## 📋 Executive Summary
ISO 22000:2018 Gap Analysis — Business Case Report ¦ تقرير تحليل الفجوات
PROJECT OVERVIEW ¦ نظرة عامة على المشروع
Project | ISO 22000:2018 Gap Analysis & Certification Roadmap
Client | Klybeck Life Sciences — Feed Additives Manufacturer, Eastern Region
Analyst | Rajaa Al-Kanawi — Wadi Solutions Consulting
Date | Q4 2024
Objective | Assess current compliance, identify critical gaps, and build a phased implementation roadmap
KEY FINDINGS ¦ النتائج الرئيسية
Finding | Status | Impact | Priority | Recommendation
Overall Compliance Score | 62.7% | 🔴 Critical | P1 | Immediate action required — 60+ days to certification
Clause 8 (HACCP) Compliance | 31% | 🔴 Critical | P1 | Rebuild HACCP system from scratch — highest risk area
Clause 6 (Planning) Compliance | 55% | 🟠 High | P2 | Develop food safety objectives and risk register
Clause 7 (Support) Compliance | 68% | 🟡 Medium | P2 | Update training records and calibration procedures
Clause 9 (Performance) Compliance | 45% | 🟠 High | P1 | Implement internal audit schedule and KPI tracking
Clause 10 (Improvement) Compliance | 52% | 🟡 Medium | P3 | Establish corrective action procedure
Documentation Gaps | 14 documents missing | 🔴 Critical | P1 | Develop all mandatory procedures within 30 days
Staff Competency | 40% trained | 🟠 High | P2 | Deliver awareness training to all food handlers

## 🔍 Gap Analysis
ISO 22000:2018 Clause-by-Clause Gap Analysis ¦ تحليل الفجوات بند ببند
ISO Clause | Requirement | Current Status | Compliance% | Gap Description | Risk Level | Recommended Action
4. Context | Understanding the organization | Partially documented | 65% | Stakeholder analysis incomplete; external issues not mapped | Medium | Complete interested parties analysis and context document
5. Leadership | Management commitment & food safety policy | Policy exists but outdated | 58% | Policy not reviewed in 2 years; food safety culture not measured | High | Update FSMS policy; conduct management review; measure FSC score
6. Planning | Risk management & objectives | Minimal documentation | 55% | No formal risk register; food safety objectives not measurable | High | Develop risk register using ISO 31000; set SMART food safety KPIs
7.1 Resources | Infrastructure & work environment | Partially compliant | 72% | Maintenance schedule exists but calibration records incomplete | Medium | Complete calibration program KLS-QP-MC-001; update equipment register
7.2 Competency | Training & awareness | Below standard | 48% | 40% of food handlers have no documented food safety training | High | Develop training matrix; deliver ISO 22000 awareness program to all staff
7.4 Communication | Internal & external comms | Basic system only | 62% | No formal communication procedure; supplier communication ad hoc | Medium | Establish communication procedure; supplier approval process
8.1 Operational Planning | PRPs & operational controls | Major gaps | 42% | PRPs documented but not validated; monitoring incomplete | Critical | Validate all PRPs against Codex standards; implement monitoring records
8.2 PRPs | Prerequisite programs | Partially implemented | 50% | 8 of 15 PRPs documented; 4 not implemented; 3 missing | High | Complete missing PRPs; implement and verify all within 45 days
8.5 HACCP | Hazard analysis & critical control points | Critical gaps | 31% | HACCP study outdated (2019); CCPs not verified; critical limits unvalidated | Critical | Rebuild complete HACCP system with current product lines
8.9 Nonconformity | NC control & corrective actions | Minimal system | 44% | No formal NC register; root cause analysis not practiced | High | Implement NC procedure; train team on RCA methods (5-Why, Fishbone)
9.1 Monitoring | Performance evaluation | Not established | 45% | No KPIs tracked; internal audits irregular; customer feedback not analyzed | High | Define FSMS KPIs; establish audit schedule; implement feedback system
9.3 Management Review | Top management oversight | Annual only | 60% | Management review held annually; no formal agenda or outputs recorded | Medium | Increase to quarterly; use structured agenda; track action items
10.1 Improvement | Continual improvement | Reactive only | 52% | Improvements made reactively; no systematic improvement program | Medium | Establish continual improvement procedure linked to KPIs
10.3 Food Safety System Update | FSMS updates | Not formalized | 55% | System updates happen informally; no change management process | Medium | Formalize change management; link to document control procedure

## 🗺️ Implementation Roadmap
ISO 22000:2018 Implementation Roadmap — 90 Days to Stage 1 Audit ¦ خارطة طريق التطبيق
Phase | Action Item | Owner | Timeline | Status | Priority | Business Impact | Effort
Phase 1 (Days 1-30) | Rebuild HACCP System — Hazard Analysis | Food Safety Team + Consultant | Days 1-15 | ⬜ Not Started | 🔴 Critical | Eliminates certification blocker | High
Phase 1 (Days 1-30) | Define CCPs and Critical Limits | Food Safety Team | Days 10-20 | ⬜ Not Started | 🔴 Critical | Core audit requirement | High
Phase 1 (Days 1-30) | Complete Missing PRPs (7 remaining) | Operations Manager | Days 1-25 | 🔄 In Progress | 🔴 Critical | Foundation of food safety system | High
Phase 1 (Days 1-30) | Deliver ISO 22000 Awareness Training | HR + Consultant | Days 5-15 | ⬜ Not Started | 🟠 High | Builds staff competency | Medium
Phase 1 (Days 1-30) | Complete Calibration Procedure (KLS-QP-MC-001) | QC Manager | Days 1-10 | ✅ Complete | 🟠 High | Measurement reliability | Medium
Phase 2 (Days 31-60) | Develop Food Safety Objectives & KPIs | Management + Consultant | Days 31-40 | ⬜ Not Started | 🟠 High | Enables performance tracking | Medium
Phase 2 (Days 31-60) | Implement NC and Corrective Action Procedure | Quality Team | Days 31-45 | ⬜ Not Started | 🟠 High | Required for ISO compliance | Medium
Phase 2 (Days 31-60) | Conduct Management Review | CEO + Management | Day 45 | ⬜ Not Started | 🟠 High | Demonstrates leadership commitment | Low
Phase 2 (Days 31-60) | Validate all Monitoring Records (30 days data) | Operations | Days 31-60 | ⬜ Not Started | 🔴 Critical | Audit evidence requirement | High
Phase 2 (Days 31-60) | Update Food Safety Policy | CEO | Days 31-35 | ⬜ Not Started | 🟡 Medium | Governance document | Low
Phase 3 (Days 61-90) | Conduct Full Internal Audit | Internal Auditor | Day 65-70 | ⬜ Not Started | 🔴 Critical | Pre-Stage 1 readiness check | High
Phase 3 (Days 61-90) | Address Internal Audit Findings | All Departments | Days 71-80 | ⬜ Not Started | 🔴 Critical | Close gaps before external audit | High
Phase 3 (Days 61-90) | Stage 1 Documentation Audit (AQC) | Certification Body | Day 85-90 | ⬜ Not Started | 🔴 Critical | First official certification step | High
Phase 3 (Days 61-90) | Prepare Stage 2 Action Plan | Consultant + Management | Day 90 | ⬜ Not Started | 🟠 High | Roadmap post Stage 1 | Medium

## 📊 Compliance Scorecard
Compliance Scorecard & Progress Tracker ¦ بطاقة الأداء والتتبع
ISO Clause | Clause Name | Baseline % | Target % | Current % | Gap to Close | RAG Status
Clause 4 | Context of Organization | 65% | 90% | 65% | 25% | 🟡 Progressing
Clause 5 | Leadership & Commitment | 58% | 90% | 62% | 28% | 🟠 At Risk
Clause 6 | Planning | 55% | 90% | 58% | 32% | 🟠 At Risk
Clause 7 | Support & Resources | 68% | 90% | 70% | 20% | 🟡 Progressing
Clause 8.1-8.4 | Operational Planning | 42% | 85% | 45% | 40% | 🔴 Critical
Clause 8.5 | HACCP System | 31% | 90% | 35% | 55% | 🔴 Critical
Clause 8.9 | Nonconformity Control | 44% | 85% | 48% | 37% | 🔴 Critical
Clause 9 | Performance Evaluation | 45% | 90% | 50% | 40% | 🟠 At Risk
Clause 10 | Improvement | 52% | 90% | 55% | 35% | 🟠 At Risk
OVERALL | ISO 22000:2018 Total Compliance